## Cover Sheet
NHSE SW Region Clinical Risk Management Pilot Approach for primary care AVT deployments
Every organisation is accountable for the clinical safety of the software it uses. This means that each practice must be able to provide evidence that they have thought about risk and are using the software safely.
This AVT approach is based on the System-level Approach to Clinical Risk Management developed by the South West Region, and approved by the constituent ICBs. It has been produced to support practices and PCNs who wish to ensure that they deploy and use AVT Software safely and in compliance with DCB 0160.
Please remember that neither the SW Region nor ICBs can be accountable for locally-procured and assured software and cannot automatically endorse outputs of this approach. However, the SW Region will support practices who choose to use this approach with advice and guidance from the CRM team.
The approach does not require that each practice has to undertake its own clinical safety activities. It is designed to allow a number of organisations to undertake a system-level approach, provided that they are deploying the software for the same intended use and that they enter into an agreement to work as a system.
The approach does require that you undertake a pilot
It consists of a series of six templates, and information on known AVT hazards, to help you capture and communicate the evidence you need to demonstrate safe practice.
Fields are not mandatory. You can adapt every template to suit your particular needs. What you are aiming to do is to clearly communicate what the software does, what you are using it for and how you are using it safely.
Your audience is your patients, your colleagues and bodies such as CQC |  | The South West System-level Approach to Clinical Risk Management
Owner: | NHSE SW Region
Authors: | Maggie Lay, Stephen Roche
Date of release: | 03.07.2025
Version number: | 1.2
© Maggie Lay, Stephen Roche, 2025, NHSE/NHS SCW. All rights reserved. This model and associated materials are made available for non-commercial use by NHS organisations and public sector bodies in England. You may reproduce and adapt these materials for internal purposes, provided that: - You credit the original author as follows: - “Based on the NHSE SW Regional Clinical Risk Management Pilot Approach for primary care, developed by Maggie Lay and Stephen Roche, 2025.” - You do not charge any fee for access or resale of this material. Any commercial use, including but not limited to reproduction, adaptation, or distribution for profit, consultancy services, or inclusion in commercial software products, is prohibited without prior written permission. To request permission for commercial use, contact england.swaicollaboration@nhs.net.

## The pilot approach
The pilot approach
A pilot is a limited-scale, time-bound trial of new healthcare software, conducted in a real-world NHS setting to evaluate performance, safety, usability, and impact prior to wider implementation.
The key features of a pilot are:
Controlled Scope
Trialed in a small number of sites, departments, or with selected users
Real-world Testing
Assesses functionality in live clinical settings
Risk Mitigation
Identifies and addresses issues before full-scale rollout
Evaluation Focus
Gathers user feedback, monitors clinical impact, and checks integration
Standards-Based
Aligned with NHS digital safety standards (e.g., DCB0129 / DCB0160)
A structured pilot is the key element of the NHSE SW Region approach to clinical risk management for AVT.
The system-level approach
If the pilot is being undertaken by more than one practice, the following elements are required:
An agreement between organisations to act as a system
This is covered in the overview and governance template
A common software
You are testing the same software
A common purpose
You are going to be using the software for the same clinical reasons
The outputs of a pilot cannot be used as evidence supporting a wider deployment without all three elements being in place

## 1. Overview and governance
| #VALUE! | The purpose of this template is to ensure that all participating organisations agree about what it is they are trying to do in the pilot and where the risk ownership sits | Template completed by:
Template approved by:
Template last updated on:
What we are trying to do (the common purpose):
Eg improving existing admin or clinical processes; designing a new service. Consider baseline measurements if necessary | Description of requirement or opportunity
What we are using:
AVT Software name
Please note: the Region strongly advises that you do not deploy health software that does not meet this standard. Please contact the CRM team if you have any questions about this. | Has the manufacturer provided a DCB0129 Clinical Safety Case Report and Hazard Log that you can understand?
Who we are:
Name of Practice/PCN/Group
Names of all participating practices
Names of any other participating organisations
Who is responsible for what:
Risk ownership
Who is paying for this?
Who owns the clinical risk for each participating organisation?
It is really important that all participating organisations have the opportunity to be represented and that they formally agree to accept the recommendations. If they do not, they cannot rely on the outputs of the pilot for their organisational compliance obligations. You may wish to consider a formal MOU document, or you may consider the information captured on this template to be sufficient. | Are all participating organisations represented?
Have all organisations agreed to accept the decisions and recommendations made by the leadership?

## 2. Pre-pilot assurance
#VALUE! | The purpose of this template is to help you think about how the software will help you achieve your common purpose (benefits, risks and unintended consequences) and how you will test this in the pilot (pilot objectives) | [5 empty] | Template completed by:
Template approved by:
Template last updated on:
Your pilot objectives should be summarised in your PILOT PLAN
Common Purpose
Benefits
What can the AVT software do to help achieve your common purpose? |  | #1 | #2 | #3 | #4 | #5
> What are your pilot objectives to test this functionality?
Gaps
What does the AVT software NOT do to help you achieve your common purpose? |  | #1 | #2 | #3 | #4 | #5
> What are your pilot objectives to test for gaps?
What else might you need to do to help you achieve your common purpose? |  | #1 | #2 | #3 | #4 | #5
> What are your pilot objectives to identify additional processes and software?
Unintended consequences
What other purposes could the software be used for? |  | #1 | #2 | #3 | #4 | #5
Pilot objectives to identify what other purposes the software might be used for
What clinical harm might arise as a result? |  | #1 | #2 | #3 | #4 | #5
How might you stop that?
> Pilot objectives to identify and assess harm
> Pilot objectives to identify controls and mitigations

## AVT known hazards log
#VALUE! |  | The information on this page has been sourced from PCNs and practices within the SW Region who have already carried out initial hazard identification activities. Those hazards have been collated and risk assessed by regional CSOs. We will add to this body of information as we receive feedback from pilots. Not all hazards will be applicable to all software and all pilots. Where hazards are applicable to your pilot, you need to provide evidence that you have taken steps to reduce the likelihood of the harm occuring during the pilot. We have made suggestions in red capitals about how you might capture that evidence
Your plans for providing evidence should be contained in your PILOT PLAN
Hazard #1 |  |  | Hazard #2 |  |  | Hazard #3 |  |  | Hazard #4 |  |  | Hazard #5
User cannot use AVT |  | Harm: No patient harm | AVT outputs are delayed |  | Harm: Delayed care | AVT system does not correctly capture or summarise the conversation |  | Harm: Delayed, inappropriate, or failure of, care | Consulatation is not saved to the correct EPR record |  | Harm: Delayed, inappropriate, or failure of, care | EPR entry is incorrect, contains errors, or contains omissions |  | Harm: Delayed, inappropriate, or failure of, care
Potential causes |  | Pilot actions | Potential causes |  | Pilot actions | Potential causes |  | Pilot actions | Potential causes |  | Pilot actions | Potential causes |  | Pilot actions
1a | User forgets login details | User knows how to reset password User knows to revert to traditional methods of capturing information PILOT USER GUIDE | 2a | High system load | Pilot testing PILOT TEST LOGS User knows to revert to traditional methods of capturing information PILOT USER GUIDE | 3a | Clinician does not press start | User has been trained to use the system PILOT TRAINING LOG User understands the clinical risk of not using the system properly PILOT USER GUIDE PILOT USER AGREEMENT | 4a | More than one record open concurrently | User has been trained to use the system PILOT TRAINING LOG User understands the clinical risk of not using the system properly PILOT USER GUIDE PILOT USER AGREEMENT | 5a | Clinician does not review AVT system consultation summary | User has been trained to use the system PILOT TRAINING LOG User understands the clinical risk of not using the system properly PILOT USER GUIDE PILOT USER AGREEMENT
1b | User isn't authorised to access AVT system (not part of pilot) | User knows to revert to traditional methods of capturing information PILOT USER GUIDE | 2b | Poor internet connectivity or interruptions during generation |  | 3b | Clinican presses pause during consultation and does not re-start it |  | 4b | Consultation summary copied incorrectly/imcompletely |  | 5b | Clinican reviews AVT system summary, but misses errors
1c | Loss of internet connectivity |  |  |  |  | 3c | Clinician does not press stop |  | 4c | Incorrect local system configuration | Pre-pilot testing PILOT TEST LOGS | 5c | Clinician does not review AVT system summary in a timely manner
1d | Local IT failure |  |  |  |  | 3d | Clinician selects dictate instead of transcribe |  | 4d | Error in AVT system operation | Pilot testing PILOT TEST LOGS Pilot incident management process PILOT USER GUIDE | 5d | Clinician cannot recall consultation detail in order to check/correct/manually enter
1e | AVT supplier system is down/unavailable |  |  |  |  | 3e | Clinician does not verbalise all consultation information, or fails to manually add it once consultation ends. |  |  |  |  | 5e | Clinician reliance on AI output (verification fatigue, or system trust)
1f | Authorised pilot user has not been trained in system use | User training PILOT TRAINING LOG |  |  |  | 3f | Clinician selects inappropriate template |  |  |  |  | 5f | AVT system bias | Pilot testing PILOT TEST LOGS Pilot incident management process PILOT USER GUIDE
[6 empty] | 3g | Technical Issues (e.g., microphone quality) | Pre-pilot testing Pilot testing PILOT TEST LOGS |  |  |  | 5c | AVT system overt/covert influence on clinical decision-making
[6 empty] | 3h | Environmental issues (background noise, consultation interruptions, language issues)
[6 empty] | 3i | Transcribing/summarisation error by AVT system | Pilot testing PILOT TEST LOGS Pilot incident management process PILOT USER GUIDE
[6 empty] | 3j | AVT system AI hallucinations
[6 empty] | 3k | Misinterpretation of ambiguous medical terminology
[6 empty] | 3l | Follow up command requested but not accurately incorporated into summary

## 3. Pilot plan (original) (hidden)
| #VALUE! | This section describes how you will run the pilot, based on the information identified in the previous templates and the known AVT hazards. Please remember that these are suggested fields only. Complete what is relevant to you, and add additional fields as necessary. The most important thing is that you communicate clearly what you are hoping to achieve and how you are going to do it. Your audience is your patients, your colleagues and bodies such as CQC | Template completed by:
Template approved by:
Template last updated on:
Suggested information to include: | 1. Product overview
How the software works.
What it does do
What it doesn’t do.
Assumptions
Handed over risks from DCB 0129
2. Pilot scope
How long will the pilot last?
Consider a PILOT TEST LOG | What is being tested?
What is not being tested?
3. Pilot objectives
*This section can be adapted to reflect the specific requirements of the pilot Suggested information to include: | 4. Pilot information
Pilot leadership
Who is leading the pilot?
Is there a pilot leadership group?
How will the leadership communicate with the participants?
Responsibilities and accountability
Who is responsible for what in the pilot?
How will decisions be made and recorded?
Participants
Who will be using the software?
Remember! This is a pilot. Participants must agree not to rely on the software and to commit to the pilot objectives. Consider having a PILOT USER AGREEMENT for for participants to sign | Are participants aware of their responsibilities in undertaking this pilot? How will this be communicated?
Incident management
What is the incident management process for the pilot?
Feedback
How will participants feed back to the leadership?
Training
Consider a TRAINING LOG | What training will people need before they start?
Processes and protocols
Consider a PILOT USER GUIDE | Processes and protocols necessary to ensure the safe use of the software during the pilot, based on the AVT known hazards

## 3. Pilot plan
| #VALUE! | This section describes how you will run the pilot, based on the information identified in the previous templates and the known AVT hazards. Please remember that these are suggested fields only. Complete what is relevant to you, and add additional fields as necessary. The most important thing is that you communicate clearly what you are hoping to achieve and how you are going to do it. Your audience is your patients, your colleagues and bodies such as CQC | Template completed by:
Template approved by:
Template last updated on:
Suggested information to include: | 1. Product overview
How the software works.
What it does do
What it doesn’t do
Assumptions
The Medical Device status of the software
2. Handed over risks from the AVT manufacturer's DCB 0129
In most cases, the manufacturer of the AVT product you are piloting will hand over or transfer certain risks and mitigations to the end-user. This information should be found in the AVT manufacturer's DCB 0129 hazard log and/or clinical safety case report. Record here the handed over risks, the suggested mitigations, and what you intend to do about them. It is recommended to seek CSO advice if the risks or mitigations are unclear or cannot be found.
3. Pilot scope
How long will the pilot last?
Consider a PILOT TEST LOG | What is being tested?
What is not being tested?
4. Pilot objectives
*This section can be adapted to reflect the specific requirements of the pilot Suggested information to include: | 5. Pilot information
Pilot leadership
Who is leading the pilot?
Is there a pilot leadership group?
How will the leadership communicate with the participants?
Responsibilities and accountability
Who is responsible for what in the pilot?
How will decisions be made and recorded?
Participants
Who will be using the software?
Remember! This is a pilot. Participants must agree not to rely on the software and to commit to the pilot objectives. Consider having a PILOT USER AGREEMENT for for participants to sign | Are participants aware of their responsibilities in undertaking this pilot? How will this be communicated?
Incident management
What is the incident management process for the pilot?
Feedback
How will participants feed back to the leadership?
Training
Consider a TRAINING LOG | What training will people need before they start?
Processes and protocols
Consider a PILOT USER GUIDE and PILOT USER AGREEMENT | Processes and protocols necessary to ensure the safe use of the software during the pilot, based on the AVT known hazards

## 4. Additional hazards
#VALUE! | The purpose of this template is to capture additional hazards you identify during and after the pilot, and to help you identify effective ways to manage (mitigate) them. You may need help from the CRM team to use this template effectively. | [7 empty] | Template completed by:
| The hazards and mitigations you identify here will inform your Post-Pilot Review | [7 empty] | Template approved by:
| They will also help you complete your Local Implementation Documentation, if you decide to deploy | [7 empty] | Template last updated on:
They will also help the Programme to update its known AVT hazard logs and to share knowledge and best practice across the region
Additional hazard #1 |  | Additional hazard #2 |  | Additional hazard #3 |  | Additional hazard #4 |  | Additional hazard #5
Description | Harm | Description | Harm | Description | Harm | Description | Harm | Description |  | Harm
Causes | Required action | Causes | Required action | Causes | Required action | Causes | Required action | Causes |  | Required action
1a |  | 2a |  | 3a |  | 4a |  | 5a
1b |  | 2b |  | 3b |  | 4b |  | 5b
1c |  | 2c |  | 3c |  | 4c |  | 5c
1d |  | 2d |  | 3d |  | 4d |  | 5d
1e |  | 2e |  | 3e |  | 4e |  | 5e
1f |  | 2f |  | 3f |  | 4f |  | 5f
1g |  | 2g |  | 3g |  | 4g |  | 5g

## 5. Post-pilot review
| #VALUE! | The purpose of this template is to document your decisions to proceed, based upon what you learnt in the pilot. You may only need to answer the first two questions, if you can clearly explain your reasons. Or you may find it useful to structure your reasons based on the questions in the second table. For complex deployments, you may find a full hazard log to be a useful tool. Please ask the CRM team for advice |  |  | Template completed by:
Template approved by:
Template last updated on:
| Decisions |  |  | Reasons
Will we use this software for this common purpose?
If yes, then what are the governance arrangements for BAU?
| Questions to consider |  | For complex questions and decisions, a hazard log will probably be helpful. Please ask the CRM team for help with this.
Were we able to test all the functionality during the pilot?
Was the pilot sufficent to meet the objectives?
What was learnt?
What benefits were proved?
Ensure these are added to '4. Additional hazards' template | What harms were revealed?
What harms were we able to mitigate?
Are your mitigations suitable for the long term? | Are they sustainable ?
What harms were we not able to mitigate?
Consider the clinical consequences | What's the worst that can happen if these harms continue?

## 6.Local Implementation Document
This template is the Clinical Safety Case Report It should be tailored to reflect the learning from the pilot, and to enable each organisation to provide evidence that they are using the software safely | #VALUE! | 1. The Local Implementation Document (LID) is a structured document which forms part of the Clinical Safety Case. It serves three purposes:
a) To inform individual organisations of their responsibilities to ensure that software is deployed and used safely for a defined purpose.
b) To enable those organisations to provide evidence that they have met those responsibilities.
c) To communicate to end users how they can be sure that they are using the software safely for a defined purpose
2. There are two stages to the development of the LID:
a) The adaptation of this generic LID to ensure that it reflects the specific requirements learnt during the pilot *
b) The completion and ownership of the LID by each participating organisation
1. Introduction and purpose
This [software] LID has been produced by [PCN or practice name] to describe why and how it uses the software.
This LID is version [version number]
| It has been created by: | It has been approved by:
It was last reviewed on [date].
It is intended to be used as a guide by the [Team] and to provide an introductory overview for new users.
It also part of a suite of documents produced by [PCN or practice name] to demonstrate that they are compliant with DCB0160 in respect of the deployment and use of the [Software name] software.
Suggested information to include: | 2. Product overview
How the software works.
What it does do
What it doesn’t do
Assumptions
Handed over risks from DCB 0129
3. System level information
Where appropriate describe your system and its constituent organisations. | This document is based on the output of [name of pilot], which was conducted [with/by which organisation(s), who was involved, for how long did the pilot last?]
*This section can be adapted to reflect the specific requirements learnt during the pilot Suggested information to include: | 4. Local level information
Purpose
What is the software being used for by this organisation?
People
Who will be using the software? What are their roles?
Responsibilities and accountability
Who is responsible for what in this organisation? Review the governance arrangements you made for the pilot and ensure they are fit for a wider roll-out.
Training
Training requirements and evidence Can reference other documents
Processes and protocols
Processes and protocols necessary to ensure the safey use of the software - consider your hazard controls Can reference other documents
Incident management
How you will manage incidents relating to the use of the AVT product Can reference other documents

## Validation (hidden)
Yes
No